Soulbound Ascent

Demo-First Vertical Slice Plan

Build 0 -> Build 1 -> Build 1.5 -> Build 2 -> Build 3

A stricter capstone plan that always protects a playable demo.

# Executive Summary

Keep the three-build structure, but add stricter gates and a smaller guaranteed demo path. The project should always have a playable build, even if later systems are cut.

The minimum successful capstone is: deploy heroes, watch readable auto-battle, make preparation choices, and see roster consequences.

| Build | Goal | Gate |
| --- | --- | --- |
| Build 0 | Remove setup risk immediately. | The team can open the Unity project, run the scene, and produce a build. |
| Build 1 | Prove the combat is fun enough to build around. | One floor is playable from deploy to win/loss, and the player can explain what happened. |
| Build 1.5 | Make combat reusable before town work starts. | Two floors can run from data, and the combat scene can accept external hero/floor inputs. |
| Build 2 | Make choices before battle matter. | Player can summon, train, deploy real roster heroes, clear a floor, gain XP, save/load, and return to town. |
| Build 3 | Add emotional weight without blowing up the project. | A new player can complete the demo without developer explanation. |

# Build 0: Unity Setup And First Scene

Goal: Remove setup risk immediately.

## Todo Checklist

[ ] Create Unity project in the repo.

[ ] Confirm .gitignore and Git LFS are working.

[ ] Create base folders, one combat scene, placeholder materials, and simple camera.

[ ] Make a test Windows build by the end of setup.

Gate: The team can open the Unity project, run the scene, and produce a build.

# Build 1: Combat Core

Goal: Prove the combat is fun enough to build around.

## Todo Checklist

[ ] Build 5x6 grid.

[ ] Add placeholder heroes and enemies.

[ ] Add 4-hero deployment.

[ ] Add one Floor 1 enemy config.

[ ] Add battle phases.

[ ] Add grid movement.

[ ] Add targeting.

[ ] Add damage, death, HP bars, and win/loss.

[ ] Add pause inspection.

[ ] Add combat log.

[ ] Add result screen.

## Cut From This Build

[ ] Floor 2.

[ ] Battle speed controls.

[ ] Synergies.

[ ] Type advantage polish.

[ ] Fancy VFX.

Gate: One floor is playable from deploy to win/loss, and the player can explain what happened.

# Build 1.5: Combat Hardening

Goal: Make combat reusable before town work starts.

## Todo Checklist

[ ] Add Floor 2.

[ ] Add retry.

[ ] Add battle speed controls.

[ ] Add type advantage.

[ ] Add basic hit feedback.

[ ] Refactor battle initialization so another scene can launch combat.

[ ] Fix obvious bugs and tuning issues.

Gate: Two floors can run from data, and the combat scene can accept external hero/floor inputs.

# Build 2: Preparation Loop

Goal: Make choices before battle matter.

## Todo Checklist

[ ] Add hero data model.

[ ] Add roster manager.

[ ] Add simple town hub.

[ ] Add summoning.

[ ] Add training into five jobs.

[ ] Feed job stats into combat.

[ ] Add deployment from roster.

[ ] Add battle rewards.

[ ] Add save/load here, not later.

[ ] Add Floor 3 only after roster combat works.

## Cut From This Build

[ ] Squads beyond one simple passive choice.

[ ] Synergy UI.

[ ] Deep town menus.

[ ] Equipment.

[ ] Items.

Gate: Player can summon, train, deploy real roster heroes, clear a floor, gain XP, save/load, and return to town.

# Build 3: Consequence Loop And Final Demo

Goal: Add emotional weight without blowing up the project.

## Todo Checklist

[ ] Add hero death state.

[ ] Add Shrine revival.

[ ] Add one simple consequence: either permanent loss or inheritance, not both unless ahead.

[ ] Add one item: Elixir.

[ ] Add Floors 4 and 5.

[ ] Add final boss as a strong enemy, not a new boss framework.

[ ] Add tutorial prompts.

[ ] Polish UI readability.

[ ] Add placeholder audio/VFX.

[ ] Build, playtest, fix, lock.

Gate: A new player can complete the demo without developer explanation.

# Stretch Only

These features are not core commitments and should only be added if the gated demo path is already stable.

[ ] Restaurant.

[ ] Invasion.

[ ] Advanced equipment locking.

[ ] Multiple consumables.

[ ] Multi-phase boss.

[ ] Large hero pool.

[ ] Deep inheritance.

# Hard Cut Rules

[ ] If Build 1 is late, cut all town work until combat is playable.

[ ] If Build 2 is late, cut squads, synergies, equipment, and items.

[ ] If Build 3 is late, cut Floor 5 before cutting polish/readability.

[ ] If save/load is unstable, simplify save data instead of adding new systems.

[ ] No new systems after final playtest starts.

# Final Demo Minimum

[ ] One town screen.

[ ] Summon/train heroes.

[ ] Deploy 4 heroes.

[ ] Clear 3 floors.

[ ] See at least one hero death/revival moment.

[ ] Save/load.

[ ] Final build with clear UI and no softlocks.

# Test Plan

| Scenario | Acceptance Check |
| --- | --- |
| Setup build test | Unity project opens, first scene runs, and Windows test build is produced. |
| Combat core test | One floor is playable from deploy to win/loss with pause inspection and combat log. |
| Combat hardening test | Two floors load from data and accept external hero/floor inputs. |
| Preparation loop test | Summon/train/deploy real roster heroes, clear a floor, gain XP, save/load, and return to town. |
| Consequence test | Hero death and Shrine revival work without softlocks. |
| Final demo test | New player completes the demo without developer explanation. |

# Assumptions

[ ] Three-person team.

[ ] Unity PC build.

[ ] Placeholder art is acceptable.

[ ] Grid coordinates drive gameplay.

[ ] JSON save/load is enough.

[ ] The professor/player values a complete playable loop over feature count.