## Dashboard
Soulbound Ascent - Demo-First Vertical Slice Tracker
Build | Goal | Gate | Status
Build 0 | Remove setup risk. | Project opens, scene runs, Windows build produced. | Not Started
Build 1 | Prove combat core. | One floor playable and understandable. | Not Started
Build 1.5 | Harden combat for reuse. | Two data-driven floors and external inputs. | Not Started
Build 2 | Make preparation matter. | Summon/train/deploy/save/load loop works. | Not Started
Build 3 | Finish consequence demo. | New player completes demo without explanation. | Not Started
Status | Task Count |  | Owner | Task Count
Not Started |  |  | Samuel
In Progress |  |  | Steven
Blocked |  |  | Guillermo
Done |  |  | All
Cut
Final Demo Minimum | Priority | Status
One town screen. | Must | Not Started
Summon/train heroes. | Must | Not Started
Deploy 4 heroes. | Must | Not Started
Clear 3 floors. | Must | Not Started
See at least one hero death/revival moment. | Must | Not Started
Save/load. | Must | Not Started
Final build with clear UI and no softlocks. | Must | Not Started

## All Tasks
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B0-01 | Build 0 | Create Unity project in the repo. | Samuel | M | Not Started | None | Repo contains Assets, Packages, and ProjectSettings. | Must
B0-02 | Build 0 | Confirm .gitignore and Git LFS are working. | Samuel | S | Not Started | B0-01 | Generated Unity folders are ignored and binary asset types are tracked by LFS. | Must
B0-03 | Build 0 | Create base folders, combat scene, placeholder materials, and simple camera. | Samuel/Guillermo | M | Not Started | B0-01 | First scene opens with camera, light, placeholder materials, and clean hierarchy. | Must
B0-04 | Build 0 | Make a test Windows build by the end of setup. | Guillermo | M | Not Started | B0-03 | A Windows build is produced and launches. | Must
B1-01 | Build 1 | Build 5x6 grid. | Samuel | M | Not Started | B0 Gate | Grid renders and stores coordinates/occupancy. | Must
B1-02 | Build 1 | Add placeholder heroes and enemies. | Guillermo | S | Not Started | B0 Gate | Hero and enemy placeholders are visually distinct. | Must
B1-03 | Build 1 | Add 4-hero deployment. | Steven | M | Not Started | B1-01, B1-02 | Player can deploy four heroes before battle. | Must
B1-04 | Build 1 | Add one Floor 1 enemy config. | Guillermo | S | Not Started | B1-01, B1-02 | Floor 1 enemies spawn from config. | Must
B1-05 | Build 1 | Add battle phases. | Samuel | M | Not Started | B1-03, B1-04 | Preparation, battle, victory, and defeat phases work. | Must
B1-06 | Build 1 | Add grid movement. | Samuel | M | Not Started | B1-05 | Units move cell-by-cell using grid coordinates. | Must
B1-07 | Build 1 | Add targeting. | Samuel | M | Not Started | B1-06 | Units select nearest valid target and retarget after death. | Must
B1-08 | Build 1 | Add damage, death, HP bars, and win/loss. | Samuel/Steven | M | Not Started | B1-07 | Combat resolves with visible HP, death, victory, and defeat. | Must
B1-09 | Build 1 | Add pause inspection. | Steven | M | Not Started | B1-05 | Player can pause and inspect unit stats/actions. | Must
B1-10 | Build 1 | Add combat log. | Steven | M | Not Started | B1-08 | Combat log explains attacks, damage, deaths, and outcomes. | Must
B1-11 | Build 1 | Add result screen. | Steven | S | Not Started | B1-08 | Result screen appears after victory or defeat. | Must
B15-01 | Build 1.5 | Add Floor 2. | Guillermo | S | Not Started | B1 Gate | Second floor loads from data. | Must
B15-02 | Build 1.5 | Add retry. | Steven | S | Not Started | B1-11 | Current battle can reset cleanly. | Must
B15-03 | Build 1.5 | Add battle speed controls. | Steven | S | Not Started | B1-05 | 1x/2x/4x controls work and are visible. | Should
B15-04 | Build 1.5 | Add type advantage. | Samuel | S | Not Started | B1-08 | Damage modifier is applied and logged. | Should
B15-05 | Build 1.5 | Add basic hit feedback. | Guillermo | S | Not Started | B1-08 | Hits have simple visual feedback. | Should
B15-06 | Build 1.5 | Refactor battle initialization so another scene can launch combat. | Samuel | M | Not Started | B1 Gate | Combat can accept external hero and floor inputs. | Must
B15-07 | Build 1.5 | Fix obvious bugs and tuning issues. | All | M | Not Started | B15-01:B15-06 | Two floors are readable and stable. | Must
B2-01 | Build 2 | Add hero data model. | Samuel | L | Not Started | B15 Gate | Hero stores identity, stats, job, XP, and save fields. | Must
B2-02 | Build 2 | Add roster manager. | Samuel | M | Not Started | B2-01 | Roster can add, list, select, and serialize heroes. | Must
B2-03 | Build 2 | Add simple town hub. | Steven | M | Not Started | B15 Gate | One town screen links summon, train, roster/deploy. | Must
B2-04 | Build 2 | Add summoning. | Samuel/Steven | M | Not Started | B2-01, B2-03 | Player can create raw heroes and add them to roster. | Must
B2-05 | Build 2 | Add training into five jobs. | Samuel/Steven | M | Not Started | B2-01, B2-03 | Raw heroes can become Warrior, Guardian, Archer, Mage, or Healer. | Must
B2-06 | Build 2 | Feed job stats into combat. | Samuel | M | Not Started | B2-05 | Combat stats come from trained roster heroes. | Must
B2-07 | Build 2 | Add deployment from roster. | Samuel/Steven | M | Not Started | B2-02, B2-06 | Selected roster heroes deploy into battle. | Must
B2-08 | Build 2 | Add battle rewards. | Samuel | M | Not Started | B2-07 | Victories grant XP and update floor progress. | Must
B2-09 | Build 2 | Add save/load here, not later. | Samuel | L | Not Started | B2-02, B2-08 | Roster and progress persist after restart. | Must
B2-10 | Build 2 | Add Floor 3 only after roster combat works. | Guillermo | M | Not Started | B2-07 | Third floor is playable with real roster stats. | Should
B3-01 | Build 3 | Add hero death state. | Samuel | M | Not Started | B2 Gate | Dead heroes leave normal availability after battle. | Must
B3-02 | Build 3 | Add Shrine revival. | Samuel/Steven | M | Not Started | B3-01 | Dead heroes can be revived without softlock. | Must
B3-03 | Build 3 | Add one simple consequence: permanent loss or inheritance. | Samuel | M | Not Started | B3-02 | One consequence path exists; not both unless ahead. | Should
B3-04 | Build 3 | Add one item: Elixir. | Samuel/Steven | M | Not Started | B2 Gate | Elixir auto-triggers and is consumed. | Should
B3-05 | Build 3 | Add Floors 4 and 5. | Guillermo | L | Not Started | B2-10 | Floors 4 and 5 load from data. | Should | Cut Floor 5 if late.
B3-06 | Build 3 | Add final boss as a strong enemy, not a new boss framework. | Guillermo | M | Not Started | B3-05 | Final floor has a strong readable enemy encounter. | Should
B3-07 | Build 3 | Add tutorial prompts. | Steven | M | Not Started | B2 Gate | First-time prompts explain summon, train, deploy, battle, death. | Must
B3-08 | Build 3 | Polish UI readability. | Steven | M | Not Started | B2 Gate | Core flow is readable for new players. | Must
B3-09 | Build 3 | Add placeholder audio/VFX. | Guillermo | M | Not Started | B1 Gate | Combat and UI have basic feedback. | Should
B3-10 | Build 3 | Build, playtest, fix, lock. | All | L | Not Started | B3-01:B3-09 | Final build is locked after playtest fixes. | Must

## Build 0 - Setup
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B0-01 | Build 0 | Create Unity project in the repo. | Samuel | M | Not Started | None | Repo contains Assets, Packages, and ProjectSettings. | Must
B0-02 | Build 0 | Confirm .gitignore and Git LFS are working. | Samuel | S | Not Started | B0-01 | Generated Unity folders are ignored and binary asset types are tracked by LFS. | Must
B0-03 | Build 0 | Create base folders, combat scene, placeholder materials, and simple camera. | Samuel/Guillermo | M | Not Started | B0-01 | First scene opens with camera, light, placeholder materials, and clean hierarchy. | Must
B0-04 | Build 0 | Make a test Windows build by the end of setup. | Guillermo | M | Not Started | B0-03 | A Windows build is produced and launches. | Must

## Build 1 - Combat Core
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B1-01 | Build 1 | Build 5x6 grid. | Samuel | M | Not Started | B0 Gate | Grid renders and stores coordinates/occupancy. | Must
B1-02 | Build 1 | Add placeholder heroes and enemies. | Guillermo | S | Not Started | B0 Gate | Hero and enemy placeholders are visually distinct. | Must
B1-03 | Build 1 | Add 4-hero deployment. | Steven | M | Not Started | B1-01, B1-02 | Player can deploy four heroes before battle. | Must
B1-04 | Build 1 | Add one Floor 1 enemy config. | Guillermo | S | Not Started | B1-01, B1-02 | Floor 1 enemies spawn from config. | Must
B1-05 | Build 1 | Add battle phases. | Samuel | M | Not Started | B1-03, B1-04 | Preparation, battle, victory, and defeat phases work. | Must
B1-06 | Build 1 | Add grid movement. | Samuel | M | Not Started | B1-05 | Units move cell-by-cell using grid coordinates. | Must
B1-07 | Build 1 | Add targeting. | Samuel | M | Not Started | B1-06 | Units select nearest valid target and retarget after death. | Must
B1-08 | Build 1 | Add damage, death, HP bars, and win/loss. | Samuel/Steven | M | Not Started | B1-07 | Combat resolves with visible HP, death, victory, and defeat. | Must
B1-09 | Build 1 | Add pause inspection. | Steven | M | Not Started | B1-05 | Player can pause and inspect unit stats/actions. | Must
B1-10 | Build 1 | Add combat log. | Steven | M | Not Started | B1-08 | Combat log explains attacks, damage, deaths, and outcomes. | Must
B1-11 | Build 1 | Add result screen. | Steven | S | Not Started | B1-08 | Result screen appears after victory or defeat. | Must

## Build 1.5 - Hardening
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B15-01 | Build 1.5 | Add Floor 2. | Guillermo | S | Not Started | B1 Gate | Second floor loads from data. | Must
B15-02 | Build 1.5 | Add retry. | Steven | S | Not Started | B1-11 | Current battle can reset cleanly. | Must
B15-03 | Build 1.5 | Add battle speed controls. | Steven | S | Not Started | B1-05 | 1x/2x/4x controls work and are visible. | Should
B15-04 | Build 1.5 | Add type advantage. | Samuel | S | Not Started | B1-08 | Damage modifier is applied and logged. | Should
B15-05 | Build 1.5 | Add basic hit feedback. | Guillermo | S | Not Started | B1-08 | Hits have simple visual feedback. | Should
B15-06 | Build 1.5 | Refactor battle initialization so another scene can launch combat. | Samuel | M | Not Started | B1 Gate | Combat can accept external hero and floor inputs. | Must
B15-07 | Build 1.5 | Fix obvious bugs and tuning issues. | All | M | Not Started | B15-01:B15-06 | Two floors are readable and stable. | Must

## Build 2 - Prep Loop
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B2-01 | Build 2 | Add hero data model. | Samuel | L | Not Started | B15 Gate | Hero stores identity, stats, job, XP, and save fields. | Must
B2-02 | Build 2 | Add roster manager. | Samuel | M | Not Started | B2-01 | Roster can add, list, select, and serialize heroes. | Must
B2-03 | Build 2 | Add simple town hub. | Steven | M | Not Started | B15 Gate | One town screen links summon, train, roster/deploy. | Must
B2-04 | Build 2 | Add summoning. | Samuel/Steven | M | Not Started | B2-01, B2-03 | Player can create raw heroes and add them to roster. | Must
B2-05 | Build 2 | Add training into five jobs. | Samuel/Steven | M | Not Started | B2-01, B2-03 | Raw heroes can become Warrior, Guardian, Archer, Mage, or Healer. | Must
B2-06 | Build 2 | Feed job stats into combat. | Samuel | M | Not Started | B2-05 | Combat stats come from trained roster heroes. | Must
B2-07 | Build 2 | Add deployment from roster. | Samuel/Steven | M | Not Started | B2-02, B2-06 | Selected roster heroes deploy into battle. | Must
B2-08 | Build 2 | Add battle rewards. | Samuel | M | Not Started | B2-07 | Victories grant XP and update floor progress. | Must
B2-09 | Build 2 | Add save/load here, not later. | Samuel | L | Not Started | B2-02, B2-08 | Roster and progress persist after restart. | Must
B2-10 | Build 2 | Add Floor 3 only after roster combat works. | Guillermo | M | Not Started | B2-07 | Third floor is playable with real roster stats. | Should

## Build 3 - Final Demo
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B3-01 | Build 3 | Add hero death state. | Samuel | M | Not Started | B2 Gate | Dead heroes leave normal availability after battle. | Must
B3-02 | Build 3 | Add Shrine revival. | Samuel/Steven | M | Not Started | B3-01 | Dead heroes can be revived without softlock. | Must
B3-03 | Build 3 | Add one simple consequence: permanent loss or inheritance. | Samuel | M | Not Started | B3-02 | One consequence path exists; not both unless ahead. | Should
B3-04 | Build 3 | Add one item: Elixir. | Samuel/Steven | M | Not Started | B2 Gate | Elixir auto-triggers and is consumed. | Should
B3-05 | Build 3 | Add Floors 4 and 5. | Guillermo | L | Not Started | B2-10 | Floors 4 and 5 load from data. | Should | Cut Floor 5 if late.
B3-06 | Build 3 | Add final boss as a strong enemy, not a new boss framework. | Guillermo | M | Not Started | B3-05 | Final floor has a strong readable enemy encounter. | Should
B3-07 | Build 3 | Add tutorial prompts. | Steven | M | Not Started | B2 Gate | First-time prompts explain summon, train, deploy, battle, death. | Must
B3-08 | Build 3 | Polish UI readability. | Steven | M | Not Started | B2 Gate | Core flow is readable for new players. | Must
B3-09 | Build 3 | Add placeholder audio/VFX. | Guillermo | M | Not Started | B1 Gate | Combat and UI have basic feedback. | Should
B3-10 | Build 3 | Build, playtest, fix, lock. | All | L | Not Started | B3-01:B3-09 | Final build is locked after playtest fixes. | Must

## Hard Cut Rules
ID | Rule | Applies To | Status
C-01 | If Build 1 is late, cut all town work until combat is playable. | Build 1 | Active
C-02 | If Build 2 is late, cut squads, synergies, equipment, and items. | Build 2 | Active
C-03 | If Build 3 is late, cut Floor 5 before cutting polish/readability. | Build 3 | Active
C-04 | If save/load is unstable, simplify save data instead of adding new systems. | Build 2 | Active
C-05 | No new systems after final playtest starts. | Build 3 | Active

## Stretch Only
ID | Feature | Reason Deferred | Priority | Default Status
S-01 | Restaurant | Not needed for core loop. | Stretch | Cut
S-02 | Invasion | High complexity; threatens final demo. | Stretch | Cut
S-03 | Advanced equipment locking | Adds save/edge-case complexity. | Stretch | Cut
S-04 | Multiple consumables | Ship Elixir only first. | Stretch | Cut
S-05 | Multi-phase boss | Strong single enemy is enough. | Stretch | Cut
S-06 | Large hero pool | Small readable roster is better. | Stretch | Cut
S-07 | Deep inheritance | One consequence path is enough. | Stretch | Cut

## Test Plan
ID | Scenario | Acceptance Check | Owner | Status | Result Notes
T-01 | Setup build test | Unity project opens, first scene runs, and Windows test build is produced. | Samuel/Guillermo | Not Started
T-02 | Combat core test | One floor is playable from deploy to win/loss with pause inspection and combat log. | All | Not Started
T-03 | Combat hardening test | Two floors load from data and accept external hero/floor inputs. | All | Not Started
T-04 | Preparation loop test | Summon/train/deploy real roster heroes, clear a floor, gain XP, save/load, and return to town. | All | Not Started
T-05 | Consequence test | Hero death and Shrine revival work without softlocks. | Samuel/Steven | Not Started
T-06 | Final demo test | New player completes the demo without developer explanation. | All | Not Started