## Month 1 - Combat
Task | Category | Status | Notes | Assigned To
Unity project scaffold - set up scene, camera, lighting | Setup | Pending | Create project, ortho camera (size 7), directional light | Samuel
GridManager - spawn 5x6 cell grid with zone colors | Grid | Pending | Rows 0-1 Enemy, 2-3 Neutral, 4-5 Player; 1.1 unit spacing | Samuel
GridCell - coordinates, occupancy, click detection | Grid | Pending | gridX, gridY, ZoneType, isOccupied, OnMouseDown | Samuel
GridInputHandler - highlight cell on click + console log | UI | Pending | Subscribe to GridManager.OnCellClicked, change material | Steven
Zone materials - Player (blue), Enemy (red), Neutral (grey) | Art | Pending | 3 materials in Assets/Materials/ | Guillermo
Cell_Base prefab - flat box with collider | Art | Pending | 1x0.2x1 box, BoxCollider, neutral material | Guillermo
Unit data model - HP, stats, state machine | Combat | Pending | UnitState enum (Idle/Moving/Attacking/Dead), UnitConfigSO | Samuel
Unit MonoBehaviour - events for damaged/death | Combat | Pending | currentHp, OnDamaged event, OnDeath event, TakeDamage() | Samuel
Deployment UI - 4 hero slot buttons | UI | Pending | Horizontal layout, slot selected/deselected, occupied state | Steven
Hero prefabs - 5 job-colored cubes | Art | Pending | Warrior/Guardian/Archer/Mage/Healer with distinct colors | Guillermo
Enemy prefabs - 3 enemy-shaped cubes | Art | Pending | Goblin/Skeleton/Slime with distinct colors | Guillermo
Config SOs - hero stats (5) + enemy stats (3) | Config | Pending | HP, ATK, DEF, speed values per type | Guillermo
UnitManager - spawn/despawn/hero/enemy lists | Combat | Pending | Singleton, SpawnHero(), SpawnEnemy(), List<Unit> | Samuel
Deploy heroes - click slot -> click cell -> place unit | UI | Pending | Wire DeploymentUI to UnitManager, grid occupancy check | Steven
FloorConfigSO - enemy wave data | Config | Pending | Enemy config + grid position list; loadable by scene | Guillermo
FloorLoader - read config and spawn enemies | Combat | Pending | Reads FloorConfigSO, calls UnitManager.SpawnEnemy | Guillermo
UnitMovement - cell-by-cell move toward nearest enemy | Combat | Pending | Lerp between cells, stop when adjacent (Manhattan=1), moveTimer | Samuel
EnemyAI - pick nearest hero, move toward them | AI | Pending | Subscribe to OnBattleStart, assign movement target | Guillermo
HUD - Start Battle button + phase text | UI | Pending | PREPARATION -> BATTLE IN PROGRESS, StartBattle button | Steven
BattleManager - battle flow orchestration | Combat | Pending | BattlePhase enum, events for Start/End, singleton | Samuel
TargetingSystem - pick nearest valid target | Combat | Pending | Recalculate on death, melee range = adjacent cell | Samuel
AttackSystem - damage formula, attack timer | Combat | Pending | finalDmg = max(1, atk * (1-armor%) - def), attackTimer based on atkSpeed | Samuel
DamageNumberUI - floating damage text | UI | Pending | Pool of TMP text, float up + fade over 0.8s, subscribed to OnDamaged | Steven
UnitAnimation - scale punch on attack, fade on death | Art | Pending | 1.2x/0.8x scale over 0.1s, alpha fade to 0 over 0.5s | Guillermo
WinLossDetector - all dead = victory/defeat | Combat | Pending | Check each frame during battle, fire OnBattleEnd | Samuel
ResultScreen - VICTORY/DEFEAT modal with stats | UI | Pending | Outcome title, kill counts, Restart/Continue buttons | Steven
TypeAdvantage - +20%/-10% job triangle | Combat | Pending | Warrior>Archer>Mage>Guardian>Warrior; Healer neutral | Samuel
PauseHandler - Space to toggle pause/resume | Combat | Pending | Time.timeScale toggle, OnPaused/OnUnpaused events | Samuel
InspectionPanel - unit stats on click during pause | UI | Pending | Raycast unit, show name/HP/ATK/DEF/state panel | Steven
HitVFX - white flash on damage | Art | Pending | Quad with additive material, 0.15s expand + fade | Guillermo
CombatLog - scrollable text feed of actions | UI | Pending | 'Warrior attacks Goblin for 12 damage', color-coded | Steven
Floor 1 integration + stat tuning | Integration | Pending | Full deploy->battle->win/loss with balanced stats | Guillermo
Synergy system - Job + Attribute 2-unit thresholds | Combat | Pending | 2 same job = synergy buff, UI indicator on units | Samuel
FloorConfig loader - swap floors without scene reload | Combat | Pending | Read any FloorConfig SO, index-based loading | Samuel
Floor 2 enemy config + new variant | Config | Pending | Different enemy comp, harder than Floor 1 | Guillermo
Battle speed controls - 1x/2x/4x buttons | UI | Pending | Time.timeScale buttons, visible speed indicator | Steven
Animations - attack swing, death fade polish | Art | Pending | Better timing on attack/death animations | Guillermo
Grid zone highlights - valid deployment tinting | UI | Pending | Blue player zone, red enemy zone, occupied cells distinct | Steven
Restart battle button - no scene reload | UI | Pending | Retry calls reset, same floor config | Steven
BattleManager refactor - clean init/run/teardown | Combat | Pending | No hardcoded refs, callable from outside scene | Samuel
Input guard - block actions during battle | UI | Pending | Only pause allowed during battle | Steven
Screen shake on heavy hits | Art | Pending | Camera shake on crit or hero death | Guillermo
Sprint 2 integration + bug bash | Integration | Pending | All 3 run full playthrough, file bugs | Samuel, Steven, Guillermo

## Month 2 - Hero & Town
Task | Category | Status | Notes | Assigned To
Hero data model - Star, Attribute, Job, Squad, XP | Hero | Pending | Full serializable hero class with all MVP fields | Samuel
Summoning Gate - generate raw hero with star+attribute | Hero | Pending | Weighted random star (1-5), attribute assignment, untrained state | Samuel
Town Hub scene - building buttons + navigation | UI | Pending | Clickable buildings, transitions to menus, back button | Steven
Summoning Gate UI - summon button + hero card | UI | Pending | Result display, confirm adds to roster | Steven
Placeholder building icons + town background | Art | Pending | Colored rectangle buildings with labels, simple backdrop | Guillermo
RosterManager - list of owned heroes with states | Hero | Pending | Add/remove/query by alive/dead/reviving state | Samuel
Training Facility - choose job, apply stat changes | Hero | Pending | Untrained -> job pick -> gains base stats, locked thereafter | Samuel
Level-up system - XP gain + stat growth per job | Hero | Pending | Victory grants XP, level up = stat increase per job curve | Samuel
Training Facility UI - job selection grid | UI | Pending | 5 job cards, stat preview on hover, confirm/cancel | Steven
Squad data - 2 squads/job with stats + passive | Hero | Pending | Each job has 2 SquadSOs, passive skill, level follows hero | Samuel
Squad selection UI - dropdown on hero card | UI | Pending | Compatible squads shown, selection before deploy | Steven
Floor 3 enemy config + new variant | Config | Pending | New enemy type, different formation | Guillermo
Roster -> Battle feed - chosen heroes appear at deploy | Integration | Pending | Town hero selection appears in pre-battle panel | Samuel
Job stats in combat - damage/HP/speed by job | Combat | Pending | Warrior = phys, Mage = magic, values from hero stats | Samuel
Squad passives activate in battle | Combat | Pending | Passive triggers at correct time per SquadSO | Guillermo
Roster list UI - scrollable hero grid | UI | Pending | Star, job icon, level per hero; click for detail | Steven
Hero detail panel - full stats display | UI | Pending | Equipment slot, squad, stat breakdown | Steven
Save/load system - JSON serialization | Hero | Pending | Serialize roster, town, floor progress; load restores state | Samuel
Full loop integration: Town->Roster->Deploy->Battle->Town | Integration | Pending | Complete flow without scene reload hacks | Samuel, Steven, Guillermo
Edge cases - empty roster, all dead, no resources | UI | Pending | Graceful handling of all failure states | Samuel, Steven, Guillermo
Floors 1-3 balance with real hero stats | Balance | Pending | Winnable with 4 trained heroes, tight but fair | Guillermo
Town background art pass | Art | Pending | Distinct building silhouettes, cohesive look | Guillermo

## Month 3 - Content
Task | Category | Status | Notes | Assigned To
Soul system - death creates revivable soul with expiry | Death | Pending | Dead hero -> Soul state, timer counts down, expiry = permadeath | Samuel
Shrine revival - cost and time based on hero power | Death | Pending | Resource cost, stronger = longer revive, expiry check | Samuel
Soul inheritance - permanent loss -> XP to another hero | Death | Pending | Delete dead hero, grant XP to chosen living hero | Samuel, Steven
Equipment system - personal fixed equip, enhance, repair | Equipment | Pending | Weapon/armor on job pick, enhance stats, repair durability | Samuel
Equipment locking - trapped on wipe, recovered on clear | Equipment | Pending | Party wipe = Locked state, clear floor = Recovered | Samuel
Shrine UI - soul list with timers, revive/inherit buttons | UI | Pending | Soul name, timer bar, revive cost, inheritance target picker | Steven
Equipment UI - enhance/repair/locked indicator | UI | Pending | Hero detail shows equipment, lock state visible | Steven
Blacksmith screen - equipment enhancement | UI | Pending | Select hero, see equipment, enhance with cost preview | Steven
Tower Malice - permanent deaths increase Malice level | Malice | Pending | Tracks permadeaths, each level adds pressure | Samuel
Malice effects - invasion speed, enemy stat bonus | Malice | Pending | Low = slow, Med = +stats, High = extra enemy | Samuel
Invasion system - timer triggers invasion on cleared floors | Invasion | Pending | If stalling, upper floor invades, one at a time | Samuel
Protection mode - defend invaded floor | Invasion | Pending | Same battle scene, labeled Protection, win/lose outcomes | Samuel
Invasion warning UI - popup modal | UI | Pending | 'Floor X invaded!' modal with enemy preview, fight/retreat | Steven
Malice display - icon in town HUD | UI | Pending | Tooltip shows current Malice level + effects | Steven
Invasion encounter configs - 3 variants | Config | Pending | Weaker than full floor, scale with Malice | Guillermo
Consumable item system - equip, auto-trigger in battle | Items | Pending | 1 per hero, auto-fire on trigger (HP<70%, debuff, etc.) | Steven
3 MVP items - Elixir, Cleansing Herb, Barrier Charm | Items | Pending | Each triggers correctly, effect applies, consumed | Samuel
Apothecary UI - view and equip consumables | UI | Pending | Item list, equip to hero slot, 1 per hero limit | Steven
Restaurant meal system - pre-battle buff | Items | Pending | Select meal before battle, buff applies, expires after attempt | Guillermo
Restaurant UI - meal selection with effect preview | UI | Pending | 4 meals with buff text, confirm, one active at a time | Steven
Floor 4 - enemy config + mini-boss | Config | Pending | New enemy type, boss with high HP + passive | Guillermo
Floor 5 - final boss encounter config | Config | Pending | Two phases or unique mechanic, hardest floor | Guillermo
4 meal SOs + 3 item SOs | Config | Pending | Data assets with balanced values | Guillermo
Full tower run integration - Floor 1->5 | Integration | Pending | Complete playthrough with death/revival/invasion | Samuel, Steven, Guillermo
Floor 1-5 difficulty tuning | Balance | Pending | Progressive difficulty, boss beatable | Guillermo
Edge case pass - graceful failure states | Integration | Pending | No crashes on edge cases, player can always recover | Samuel, Steven, Guillermo
Placeholder audio - SFX from free sources | Audio | Pending | Hit sounds, death, UI clicks, town ambience | Guillermo
Tutorial tooltips - first-time prompts | UI | Pending | On first summon/death/battle, tooltip shows, skippable | Steven

## Month 4 - Polish
Task | Category | Status | Notes | Assigned To
UI style pass - consistent fonts, colors, spacing | UI | Pending | All screens same palette, hover/press states, no grayboxes | Steven
Synergy panel in battle prep - active synergies | UI | Pending | Show active Job+Attribute synergies with bonus tooltip | Steven
Synergy panel in roster - what would activate | UI | Pending | Preview synergies for current deployment | Steven
Battle VFX upgrade - hit effects, death particles | Art | Pending | Better timing, screen shake configurable | Guillermo
Combat log readability - color-coded, icons | UI | Pending | Red=damage, Green=heal, Blue=buff, collapsible | Steven
Audio integration - wire SFX to events + volume slider | Audio | Pending | Every action has sound, AudioManager with volume control | Guillermo
Music - town theme + battle theme (CC licensed) | Audio | Pending | Background music, smooth crossfade | Guillermo
Balance pass - all floors, jobs, items, meals | Balance | Pending | No inferior job, items useful, floors clearable | Guillermo
Bug fixing sprint - systematic QA pass | Bugs | Pending | All critical bugs fixed, no crashes/softlocks | Samuel, Steven, Guillermo
Save/load robustness - corruption, edge cases | Bugs | Pending | Works across restarts, save on checkpoint | Steven
Loading screen - Town <-> Battle transitions | UI | Pending | Smooth loading with progress bar | Steven
Build pipeline - single-click Windows build | Build | Pending | One command produces standalone .exe | Guillermo
Documentation - gameplay guide, build instructions | Docs | Pending | README, controls, systems, asset attribution log | Guillermo
Final playtest - 3 external players | QA | Pending | Observe new players, fix 3 bug/confusion per person | Samuel, Steven, Guillermo
Presentation build - locked branch, release, demo video | Build | Pending | Standalone build, 3-min video, slide deck updated | Samuel, Steven, Guillermo