## Dashboard
Soulbound Ascent - Three Build Tracker
Build | Goal | Gate | Core Status
Build 1 | Combat is playable and understandable. | Two combat floors can be completed. | Not Started
Build 2 | Preparation choices affect battle outcomes. | Roster heroes feed into combat and persist. | Not Started
Build 3 | Wins/losses matter without scope overload. | New player can complete the demo. | Not Started
Status | Task Count |  | Owner | Task Count
Not Started |  |  | M1
In Progress |  |  | M2
Blocked |  |  | M3
Done |  |  | All
Cut
Gate | Description | Status | Notes
Gate 1 | Combat scene playable from deployment to victory/defeat. | Not Started | Build 1 acceptance gate.
Gate 2 | Two floors load from data and battle remains readable. | Not Started | Build 1 hardening gate.
Gate 3 | Town/roster loop feeds real heroes into combat. | Not Started | Build 2 gate.
Gate 4 | Save/load works across restart. | Not Started | Build 2 stability gate.
Gate 5 | Final build can be played by a new user without explanation. | Not Started | Build 3 release gate.

## All Tasks
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B1-01 | Build 1 | Create Unity project structure and CombatPrototype scene. | M1 | M | Not Started | None | Repo contains Unity project structure and scene opens cleanly. | Must
B1-02 | Build 1 | Build 5x6 grid with player, neutral, and enemy zones. | M1 | M | Not Started | B1-01 | Grid renders, stores integer coordinates, and tracks occupied cells. | Must
B1-03 | Build 1 | Add placeholder hero/enemy prefabs. | M3 | S | Not Started | B1-01 | Five hero colors and three enemy shapes are visually distinct. | Must
B1-04 | Build 1 | Add 4-hero deployment. | M2 | M | Not Started | B1-02, B1-03 | Player can place up to four heroes in player zone before battle. | Must
B1-05 | Build 1 | Add enemy Floor 1 config. | M3 | S | Not Started | B1-02, B1-03 | Floor 1 spawns enemies from config. | Must
B1-06 | Build 1 | Add battle phases: preparation, battle, victory, defeat. | M1 | M | Not Started | B1-04, B1-05 | Visible phase transitions work. | Must
B1-07 | Build 1 | Add cell-by-cell movement using grid coordinates. | M1 | M | Not Started | B1-06 | Units move toward enemies and stop in range. | Must
B1-08 | Build 1 | Add nearest-target selection and retargeting. | M1 | M | Not Started | B1-07 | Units select nearest living enemy and switch targets after death. | Must
B1-09 | Build 1 | Add attack timers, damage formula, HP, death. | M1 | M | Not Started | B1-08 | Attacks reduce HP; dead units stop acting. | Must
B1-10 | Build 1 | Add result screen. | M2 | S | Not Started | B1-09 | Victory/defeat screen appears at battle end. | Must
B1-11 | Build 1 | Add pause and unit inspection. | M2 | M | Not Started | B1-06 | Pause freezes battle and selected unit stats are visible. | Must
B1-12 | Build 1 | Add combat log and floating damage numbers. | M2/M3 | M | Not Started | B1-09 | Attacks and deaths appear in log; damage feedback is visible. | Must
B1-13 | Build 1 | Add Floor 2 config. | M3 | S | Not Started | B1-05 | Second floor loads with distinct enemy composition. | Should
B1-14 | Build 1 | Add retry and battle speed controls. | M2 | S | Not Started | B1-10 | Retry resets current floor; 1x/2x/4x controls work. | Should
B1-15 | Build 1 | Tune until 2 floors are playable. | All | M | Not Started | B1-01:B1-14 | Floor 1 and Floor 2 can be completed without console errors. | Must
B2-01 | Build 2 | Add hero data model: star, attribute, job, squad, level, XP, stats. | M1 | L | Not Started | Build 1 Gate | Hero data supports roster and combat stats. | Must
B2-02 | Build 2 | Add roster manager. | M1 | M | Not Started | B2-01 | Owned heroes can be added, listed, selected, and serialized. | Must
B2-03 | Build 2 | Add simple town hub. | M2 | M | Not Started | Build 1 Gate | Player can navigate town screens. | Must
B2-04 | Build 2 | Add Summoning Gate: generate raw heroes with star + attribute. | M1/M2 | M | Not Started | B2-01, B2-03 | Generated heroes can be confirmed into roster. | Must
B2-05 | Build 2 | Add Training Facility: choose one job for an untrained hero. | M1/M2 | M | Not Started | B2-01, B2-03 | Untrained hero can lock into a job and gain stats. | Must
B2-06 | Build 2 | Add 5 jobs: Warrior, Guardian, Archer, Mage, Healer. | M1/M3 | M | Not Started | B2-05 | All five jobs have readable stats and identity. | Must
B2-07 | Build 2 | Add job stats feeding into battle. | M1 | M | Not Started | B2-06 | Combat values come from trained hero data. | Must
B2-08 | Build 2 | Add squad choice: 1-2 squad options per job. | M1/M2 | M | Not Started | B2-06 | Compatible squad can be selected before battle. | Should
B2-09 | Build 2 | Add deployment from roster instead of hardcoded test heroes. | M1/M2 | M | Not Started | B2-02, B2-07 | Selected roster heroes appear in battle deployment. | Must
B2-10 | Build 2 | Add basic job/attribute synergy. | M1 | M | Not Started | B2-09 | Two-unit threshold applies simple stat bonus. | Should
B2-11 | Build 2 | Add battle rewards: XP and floor clear progress. | M1 | M | Not Started | B2-09 | Victories grant XP and update floor progress. | Must
B2-12 | Build 2 | Add JSON save/load. | M1 | L | Not Started | B2-02, B2-11 | Roster and floor progress persist after restart. | Must
B2-13 | Build 2 | Add Floor 3. | M3 | M | Not Started | B2-09 | Third floor loads and is tuned for roster stats. | Should
B2-14 | Build 2 | Tune floors 1-3 using real roster stats. | M3 | M | Not Started | B2-07, B2-13 | Floors 1-3 are winnable and distinct. | Must
B3-01 | Build 3 | Add hero death state after battle. | M1 | M | Not Started | Build 2 Gate | Dead heroes leave normal roster availability. | Must
B3-02 | Build 3 | Add Shrine revival with simple cost or timer. | M1/M2 | M | Not Started | B3-01 | Dead heroes can be revived without softlock. | Must
B3-03 | Build 3 | Add permanent loss only if revival is stable. | M1 | S | Not Started | B3-02 | Permanent loss path exists and is clearly warned. | Should
B3-04 | Build 3 | Add simple inheritance as XP transfer if time allows. | M1 | S | Not Started | B3-03 | A lost hero can transfer XP to a living hero. | Stretch
B3-05 | Build 3 | Add one equipment slot or fixed personal equipment. | M1 | M | Not Started | B2-01 | Equipment adds a simple stat bonus. | Should
B3-06 | Build 3 | Add equipment stat bonus. | M1 | S | Not Started | B3-05 | Equipment stat affects combat values. | Should
B3-07 | Build 3 | Add one auto-trigger item: Elixir. | M1/M2 | M | Not Started | B1-09 | Elixir triggers at low HP and is consumed. | Should
B3-08 | Build 3 | Add Floor 4 and Floor 5. | M3 | L | Not Started | B2-14 | Five floors load from config. | Must
B3-09 | Build 3 | Add final boss as a strong enemy, not a complex multi-phase fight. | M3 | M | Not Started | B3-08 | Final encounter is harder without new boss framework. | Must
B3-10 | Build 3 | Add simple Tower Malice only if death/revival is stable. | M1 | M | Not Started | B3-02 | Permanent loss increases visible pressure value. | Stretch
B3-11 | Build 3 | Add tutorial prompts for summon, train, deploy, battle, death. | M2 | M | Not Started | B2 Gate | First-time prompts cover main loop. | Should
B3-12 | Build 3 | Polish UI readability. | M2 | M | Not Started | B2 Gate | Core screens use consistent spacing, labels, and visual hierarchy. | Must
B3-13 | Build 3 | Add placeholder audio/VFX. | M3 | M | Not Started | B1 Gate | Hits, deaths, and UI actions have basic feedback. | Should
B3-14 | Build 3 | Create Windows build. | M3 | M | Not Started | B3-08, B3-12 | Standalone build launches locally. | Must
B3-15 | Build 3 | Run 3-player external playtest. | All | M | Not Started | B3-14 | Three new players attempt demo without explanation. | Must
B3-16 | Build 3 | Fix critical confusion, crashes, and softlocks. | All | L | Not Started | B3-15 | Critical issues from playtest are resolved. | Must
B3-17 | Build 3 | Lock final presentation build. | All | M | Not Started | B3-16 | Release build, demo video, and docs are ready. | Must

## Build 1 - Combat Demo
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B1-01 | Build 1 | Create Unity project structure and CombatPrototype scene. | M1 | M | Not Started | None | Repo contains Unity project structure and scene opens cleanly. | Must
B1-02 | Build 1 | Build 5x6 grid with player, neutral, and enemy zones. | M1 | M | Not Started | B1-01 | Grid renders, stores integer coordinates, and tracks occupied cells. | Must
B1-03 | Build 1 | Add placeholder hero/enemy prefabs. | M3 | S | Not Started | B1-01 | Five hero colors and three enemy shapes are visually distinct. | Must
B1-04 | Build 1 | Add 4-hero deployment. | M2 | M | Not Started | B1-02, B1-03 | Player can place up to four heroes in player zone before battle. | Must
B1-05 | Build 1 | Add enemy Floor 1 config. | M3 | S | Not Started | B1-02, B1-03 | Floor 1 spawns enemies from config. | Must
B1-06 | Build 1 | Add battle phases: preparation, battle, victory, defeat. | M1 | M | Not Started | B1-04, B1-05 | Visible phase transitions work. | Must
B1-07 | Build 1 | Add cell-by-cell movement using grid coordinates. | M1 | M | Not Started | B1-06 | Units move toward enemies and stop in range. | Must
B1-08 | Build 1 | Add nearest-target selection and retargeting. | M1 | M | Not Started | B1-07 | Units select nearest living enemy and switch targets after death. | Must
B1-09 | Build 1 | Add attack timers, damage formula, HP, death. | M1 | M | Not Started | B1-08 | Attacks reduce HP; dead units stop acting. | Must
B1-10 | Build 1 | Add result screen. | M2 | S | Not Started | B1-09 | Victory/defeat screen appears at battle end. | Must
B1-11 | Build 1 | Add pause and unit inspection. | M2 | M | Not Started | B1-06 | Pause freezes battle and selected unit stats are visible. | Must
B1-12 | Build 1 | Add combat log and floating damage numbers. | M2/M3 | M | Not Started | B1-09 | Attacks and deaths appear in log; damage feedback is visible. | Must
B1-13 | Build 1 | Add Floor 2 config. | M3 | S | Not Started | B1-05 | Second floor loads with distinct enemy composition. | Should
B1-14 | Build 1 | Add retry and battle speed controls. | M2 | S | Not Started | B1-10 | Retry resets current floor; 1x/2x/4x controls work. | Should
B1-15 | Build 1 | Tune until 2 floors are playable. | All | M | Not Started | B1-01:B1-14 | Floor 1 and Floor 2 can be completed without console errors. | Must

## Build 2 - Prep Loop
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B2-01 | Build 2 | Add hero data model: star, attribute, job, squad, level, XP, stats. | M1 | L | Not Started | Build 1 Gate | Hero data supports roster and combat stats. | Must
B2-02 | Build 2 | Add roster manager. | M1 | M | Not Started | B2-01 | Owned heroes can be added, listed, selected, and serialized. | Must
B2-03 | Build 2 | Add simple town hub. | M2 | M | Not Started | Build 1 Gate | Player can navigate town screens. | Must
B2-04 | Build 2 | Add Summoning Gate: generate raw heroes with star + attribute. | M1/M2 | M | Not Started | B2-01, B2-03 | Generated heroes can be confirmed into roster. | Must
B2-05 | Build 2 | Add Training Facility: choose one job for an untrained hero. | M1/M2 | M | Not Started | B2-01, B2-03 | Untrained hero can lock into a job and gain stats. | Must
B2-06 | Build 2 | Add 5 jobs: Warrior, Guardian, Archer, Mage, Healer. | M1/M3 | M | Not Started | B2-05 | All five jobs have readable stats and identity. | Must
B2-07 | Build 2 | Add job stats feeding into battle. | M1 | M | Not Started | B2-06 | Combat values come from trained hero data. | Must
B2-08 | Build 2 | Add squad choice: 1-2 squad options per job. | M1/M2 | M | Not Started | B2-06 | Compatible squad can be selected before battle. | Should
B2-09 | Build 2 | Add deployment from roster instead of hardcoded test heroes. | M1/M2 | M | Not Started | B2-02, B2-07 | Selected roster heroes appear in battle deployment. | Must
B2-10 | Build 2 | Add basic job/attribute synergy. | M1 | M | Not Started | B2-09 | Two-unit threshold applies simple stat bonus. | Should
B2-11 | Build 2 | Add battle rewards: XP and floor clear progress. | M1 | M | Not Started | B2-09 | Victories grant XP and update floor progress. | Must
B2-12 | Build 2 | Add JSON save/load. | M1 | L | Not Started | B2-02, B2-11 | Roster and floor progress persist after restart. | Must
B2-13 | Build 2 | Add Floor 3. | M3 | M | Not Started | B2-09 | Third floor loads and is tuned for roster stats. | Should
B2-14 | Build 2 | Tune floors 1-3 using real roster stats. | M3 | M | Not Started | B2-07, B2-13 | Floors 1-3 are winnable and distinct. | Must

## Build 3 - Consequences
ID | Build | Task | Owner | Effort | Status | Depends On | Acceptance Criteria | Priority | Notes
B3-01 | Build 3 | Add hero death state after battle. | M1 | M | Not Started | Build 2 Gate | Dead heroes leave normal roster availability. | Must
B3-02 | Build 3 | Add Shrine revival with simple cost or timer. | M1/M2 | M | Not Started | B3-01 | Dead heroes can be revived without softlock. | Must
B3-03 | Build 3 | Add permanent loss only if revival is stable. | M1 | S | Not Started | B3-02 | Permanent loss path exists and is clearly warned. | Should
B3-04 | Build 3 | Add simple inheritance as XP transfer if time allows. | M1 | S | Not Started | B3-03 | A lost hero can transfer XP to a living hero. | Stretch
B3-05 | Build 3 | Add one equipment slot or fixed personal equipment. | M1 | M | Not Started | B2-01 | Equipment adds a simple stat bonus. | Should
B3-06 | Build 3 | Add equipment stat bonus. | M1 | S | Not Started | B3-05 | Equipment stat affects combat values. | Should
B3-07 | Build 3 | Add one auto-trigger item: Elixir. | M1/M2 | M | Not Started | B1-09 | Elixir triggers at low HP and is consumed. | Should
B3-08 | Build 3 | Add Floor 4 and Floor 5. | M3 | L | Not Started | B2-14 | Five floors load from config. | Must
B3-09 | Build 3 | Add final boss as a strong enemy, not a complex multi-phase fight. | M3 | M | Not Started | B3-08 | Final encounter is harder without new boss framework. | Must
B3-10 | Build 3 | Add simple Tower Malice only if death/revival is stable. | M1 | M | Not Started | B3-02 | Permanent loss increases visible pressure value. | Stretch
B3-11 | Build 3 | Add tutorial prompts for summon, train, deploy, battle, death. | M2 | M | Not Started | B2 Gate | First-time prompts cover main loop. | Should
B3-12 | Build 3 | Polish UI readability. | M2 | M | Not Started | B2 Gate | Core screens use consistent spacing, labels, and visual hierarchy. | Must
B3-13 | Build 3 | Add placeholder audio/VFX. | M3 | M | Not Started | B1 Gate | Hits, deaths, and UI actions have basic feedback. | Should
B3-14 | Build 3 | Create Windows build. | M3 | M | Not Started | B3-08, B3-12 | Standalone build launches locally. | Must
B3-15 | Build 3 | Run 3-player external playtest. | All | M | Not Started | B3-14 | Three new players attempt demo without explanation. | Must
B3-16 | Build 3 | Fix critical confusion, crashes, and softlocks. | All | L | Not Started | B3-15 | Critical issues from playtest are resolved. | Must
B3-17 | Build 3 | Lock final presentation build. | All | M | Not Started | B3-16 | Release build, demo video, and docs are ready. | Must

## Stretch Only
ID | Feature | Reason Deferred | Priority | Default Status
S-01 | Restaurant meals | Nice strategic layer, but not required to prove the core loop. | Stretch | Cut
S-02 | Invasion/protection mode | High complexity; only add after consequence loop is stable. | Stretch | Cut
S-03 | Multiple consumable types | Ship Elixir first; expand only if item flow works. | Stretch | Cut
S-04 | Advanced equipment locking/recovery | Can create edge cases and save complexity. | Stretch | Cut
S-05 | Multi-phase final boss | Use a strong single-phase boss for the demo. | Stretch | Cut
S-06 | Deep inheritance stat bonuses | XP transfer is enough for capstone scope. | Stretch | Cut
S-07 | Large hero pool | A small readable roster is better for a vertical slice. | Stretch | Cut

## Test Plan
ID | Scenario | Acceptance Check | Owner | Status | Result Notes
T-01 | Combat test | Deploy 4 heroes and clear/lose Floor 1 and Floor 2 repeatedly. | All | Not Started | No console errors; victory/defeat resolves.
T-02 | Readability test | Pause during battle and confirm the player can explain current unit actions. | M2 | Not Started | Player can explain why a unit is moving, attacking, or dead.
T-03 | Preparation test | Two different job/squad setups produce visibly different outcomes. | M1/M3 | Not Started | Different prep choices change battle results or stats.
T-04 | Save/load test | Summon, train, save, quit, load, and confirm roster/floor progress persists. | M1 | Not Started | Loaded state matches saved state.
T-05 | Consequence test | Hero death leads to revival flow without softlock. | M1/M2 | Not Started | Dead hero can be revived or handled clearly.
T-06 | Build test | Windows build runs on another machine. | M3 | Not Started | Build launches outside dev machine.
T-07 | Playtest | Three new players complete the demo or reveal where they get stuck. | All | Not Started | Confusion and critical issues are logged and triaged.